## Acceptance Criteria
Sprint 1 — Acceptance Criteria
Inclusive Public Transport Companion ¦ QA: I — De Silva
ID | Feature | Given | When | Then | Owner (Dev) | Status
AC-01 | Registration | a new user on the Registration screen | they enter a valid name, email, and password and submit | an account is created in Firebase Auth and a matching user document appears in Firestore, then they land on Home | Wijesooriya / Divyanjana | Verified
AC-02 | Registration | a user enters an email that is already registered | they submit the form | a clear error message is shown and no duplicate account is created | Wijesooriya | Verified
AC-03 | Registration | a user enters an invalid email format or a weak password | they submit the form | an inline validation error appears immediately; no crash, no silent failure | Thiwanka / Wijesooriya | Verified
AC-04 | Login | a registered user on the Login screen | they enter valid credentials and submit | they are authenticated and redirected to Home | Wijesooriya | Verified
AC-05 | Login | a user enters a wrong password or unregistered email | they submit the form | a clear, non-technical error message appears and they remain on Login | Wijesooriya | Verified
AC-06 | Login | a user leaves the email or password field empty | they attempt to submit | the submit action is blocked and a validation message is shown | Thiwanka / Wijesooriya | Verified
AC-07 | Logout | a logged-in user on Home | they tap Logout | their session is cleared and they are redirected to Login; pressing Back does not return them to Home | Wijesooriya | Verified
AC-08 | Navigation | any screen in the app | the user taps a navigation element (button, link, back arrow) | they land on the correct destination screen with no dead ends or broken links | Thiwanka | Verified
AC-09 | Accessibility | a user with limited dexterity, mobility, or reduced vision (e.g. wheelchair users, seniors) | they use the app with larger system font/display settings or need to reach key actions one-handed | tap targets are comfortably sized, key actions are reachable one-handed, and the app remains usable at larger font/display sizes | Thiwanka | Open

## Test Cases
Sprint 1 — Test Cases
Registration / Login / Logout / Navigation
Test ID | Module | Test Case | Steps | Expected Result | Actual Result | Status | Linked AC | Tested By | Date
REG-01 | Registration | Successful registration with valid data | 1. Open Register screen 2. Enter valid name, email, password 3. Tap Submit | Account created in Firebase Auth + Firestore; user redirected to Home |  | Not Run | AC-01
REG-02 | Registration | Duplicate email registration | 1. Open Register 2. Enter an already-registered email 3. Submit | Error message shown; no duplicate account created |  | Not Run | AC-02
REG-03 | Registration | Empty fields on registration | 1. Open Register 2. Leave all fields empty 3. Tap Submit | Validation errors shown; form does not submit |  | Not Run | AC-03
REG-04 | Registration | Weak password rejected | 1. Open Register 2. Enter valid name/email 3. Enter weak password e.g. '123' 4. Submit | Password strength error shown; account not created |  | Not Run | AC-03
REG-05 | Registration | Invalid email format rejected | 1. Open Register 2. Enter 'notanemail' 3. Submit | Inline email format error shown |  | Not Run | AC-03
LOG-01 | Login | Successful login with valid credentials | 1. Open Login 2. Enter valid email/password 3. Submit | User authenticated and redirected to Home |  | Not Run | AC-04
LOG-02 | Login | Login with wrong password | 1. Open Login 2. Enter valid email, wrong password 3. Submit | Clear error shown; user stays on Login |  | Not Run | AC-05
LOG-03 | Login | Login with non-existent email | 1. Open Login 2. Enter unregistered email 3. Submit | Clear error shown; user stays on Login |  | Not Run | AC-05
LOG-04 | Login | Empty field validation | 1. Open Login 2. Leave email or password blank 3. Attempt submit | Submit blocked; validation message shown |  | Not Run | AC-06
OUT-01 | Logout | Logout clears session | 1. Log in 2. From Home, tap Logout | Redirected to Login; session cleared |  | Not Run | AC-07
OUT-02 | Logout | Back button after logout | 1. Log out 2. Press device Back button | User is NOT returned to Home; stays on/near Login |  | Not Run | AC-07
NAV-01 | Navigation | Register <-> Login links | 1. From Login, tap 'Create account' 2. From Register, tap 'Already have an account' | Both links navigate to the correct screen |  | Not Run | AC-08
NAV-02 | Navigation | Home back button behavior | 1. Log in to Home 2. Press device Back button | App does not crash or return to Login unexpectedly |  | Not Run | AC-08
ACC-01 | Accessibility | Large font/display scaling support | 1. Increase system font size and display size to maximum (Settings > Display > Font size) 2. Open Login, Register, and Home screens | All text remains readable and unclipped; no buttons or labels overlap or become unusable |  | Not Run | AC-09
ACC-02 | Accessibility | Tap target size and one-handed reachability | 1. Inspect buttons/links on Login, Register, Home 2. Attempt to complete Login and Logout using only one hand/thumb | All tap targets meet minimum comfortable size (approx 48x48dp); key actions reachable one-handed |  | Not Run | AC-09
Status legend: Pass = green, Fail = red, Blocked = grey, Not Run = white

## Bug Tracker
Sprint 1 — Bug Tracker
Log every failed test case here and link back to the dev's Jira ticket
Bug ID | Title | Related Test ID | Steps to Reproduce | Expected | Actual | Severity | Status | Reported By | Assigned To | Date Reported | Date Fixed | Retested?
BUG-01 | Login fails silently with wrong password — no error shown | LOG-02 | 1. Enter valid email 2. Enter wrong password 3. Tap Login | Clear error message shown, user stays on Login | Screen freezes for 1s, no message, button re-enables | High | Open | De Silva | Wijesooriya | 2026-08-24 |  | No

## Sprint Summary
Sprint 1 — QA Summary
Fill in during Sprint Review
Total Test Cases | 15
Passed | 0
Failed | 0
Blocked | 0
Not Run | 15
Open Bugs (Blocker/High) | 1